## Sheet1
Natural Seep Water Sampling - M/V Ryan Chouest - Daily Report

Date:		9/17/2010	Sampler:	David Shinn		Contact #:	248-990-7416
Cruise Number:		RC016	Vessel:	Ryan Chouest		Sat Phone #:	n/a

Time	Location/Coordinates	Report #	Sample Taken / Yes/No	Sample #	Picture Taken / Yes/No	Recoverable Oil / Yes/No	Comments/Notes
6:00	n/a	n/a	No	n/a	No	No	Safety Briefing
6:30	n/a	n/a	No	n/a	No	No	Ships Crew and C&C Team performing scans for initial target location.
9:04	29.05041, -88.61534	n/a	No	n/a	No	No	Reference Waypoint acquired, WP01
13:30	n/a	n/a	No	n/a	No	No	Arrive initial target area and begin patterning over target area to pinpoint CTD drop area.
14:10	n/a	n/a	No	n/a	No	No	JHA briefing performed by C&C personnel in preparation for deployment of CTD.
14:11	n/a	n/a	No	n/a	No	No	Weather Observation- PT Cloudy, Temp. 82deg, Winds SSE @ 13 knots, Seas 4-6 feet.
15:08	28.85053, -88.90221	n/a	No	n/a	Yes	No	Begin Cast at Station RC001.
15:31	28.85053, -88.90221	n/a	Yes	n/a	No	No	Sample SW-20100917-RC016-01 acquired at depth of 428m. Sample retained pending results of on-board screening. Sample label time in GMT (+5hrs)
15:33	28.85053, -88.90221	n/a	Yes	n/a	No	No	Sample SW-20100917-RC016-02 acquired at depth of 415m. Sample to be retained pending results of on-board screening. Sample label time in GMT (+5hrs)
15:34	28.85053, -88.90221	n/a	Yes	n/a	No	No	Sample SW-20100917-RC016-03 acquired at depth of 402m. Sample to be retained pending results of on-board screening. Sample label time in GMT (+5hrs)
15:36	28.85053, -88.90221	n/a	Yes	n/a	No	No	Sample SW-20100917-RC016-04 acquired at depth of 328m. Sample to be retained pending results of on-board screening. Sample label time in GMT (+5hrs)
15:38	28.85053, -88.90221	n/a	Yes	n/a	No	No	Sample SW-20100917-RC016-05 acquired at depth of 224m. Sample to be retained pending results of on-board screening. Sample label time in GMT (+5hrs)
16:28	n/a	n/a	No	n/a	Yes	No	Sample collection completed. Continue sample preparation, and place in refrigerated storage.
20:35	n/a	n/a	No	n/a	Yes	No	Vessel is attempting to acquire target area #2 for casting on 9/18.
					END REPORT