## Voyage Plan
R/V Brooks McCall

Voyage Plan

22-May-10

General

Client:				BP Oil Spill Trustees
Purpose/Job:				J10852 Leg 4
Area:				Block 252 Mississippi Canyon, GOM

From:		Fourchon, La					To:	Fourchon, La.
Estimated Duration:					4		Days			230		Miles

Estimated Consumables

Fuel				Required:		900		gal/day				On Board:		20489		gal.
Lube Oil				Required:		5		gal./day				On Board:		526		gal.
Water				Required:		1200		gal./day				On Board:		47000		gal.

Plan Implementation

			Course to be Steered					135 degrees to 1st waypoint from Fourchon Sea Buoy
			Distance on Course					34 nm to 1st site from Fourchon Sea Buoy
Departure			Tidal Depth / Currents					N/A
5/22/10			Port Clearance					N/A
			Pilot Requirements					N/A
			NTMs					Up to date through 22/10
Enroute			Safe Distances					N/A
			Prohibited Zones					Loop Terminal (Boundaries on KNav plotter, 1116A)
			Critical Depth Areas					N/A
			Contingency Ports					N/A
			NTMs					Up to date through 19/10
			Course to be Steered					215 degrees from last waypint to Fourchon Sea Buoy
			Distance on Course					34 nm from last waypoint from Fourchon Sea Buoy
Arrival			Pier / Anchorage					Fouchon
5/26/10			Agent					N/A
			Tidal Depth / Currents					N/A
			Customs / Clearance					N/A
			Pilot Requirements					N/A
			NTMs					Up to date through 22/10

Charts and Publications

Departure					1116A, 11365
Enroute-Contingency					1116A, 1115A, 11365, 11361
Arrival					1116A, 11365

Waypoints

#	Location ID					Latitude					Longintude
1	WPT001					28 54.00' N					89 52.00' W
2	WPT002					28 37.70' N					89 33.00' W
3	Mississippi Canyon 252					28 43.00' N					88 22.00' W

Operational Contraints

Type of Operation				Special Considerations
Sampling etc.				SIMOPS with other vessels and operations in the area.

Required Reports

Daily Position Report at Midnight

Email to:		DPR Group
LAT		Position latitude
LON		Position longitude
FC		Fuel Consumed in the Last 24 hrs.
FOROB		Fuel Remaining on Board
LOC		Lube Oil Consumed in the Last 24 hrs.
LOROB		Lube Oil Remaining On Board
WC		Water Consumed in the Last 24 hrs.
WROB		Water Remaining On Board
ETA		Estimated Time of Arrival at Next Waypoint or Port

Client Reports

Email to:				Dr. Jim Brooks, DPR Group
Responsibility of				James Howell
Frequency				Each day - 24 hrs.
Format / Content				Client Specific

Incident Reports

Email to:		- CC: DPR Group
Responsibility of				Captain
Send by				Within 24 hrs. of Incident
Format / Content				TDI HSE Reporting Form

Master:

R/V Brooks McCall

Crew Manifest

May 22, 2010

FD = Foc'sle Deck					MD = Main Deck					LL = Lower Level

#	Name					Title					Room #
1	Opel, Chris					Master					F3
2	Majni, Geno					Chief Mate					F2
3	Munro, Scott					2nd Mate					F1
4	Kamal, Wasib					Engineer					MD4
5	McCluskey, Ben					Oiler					LL16
6	Felix, Frank					A/B					LL17
7	Majni, Ann					OS					F2
8	Narcisis, Paul					Cook					MD5
9	Howell, James					Party Chief					LL12
10	Clark, Paul					CTD Tech					LL15
11	Green, Billy					Winch Operator					LL15
12	Lane, Larry					Deck					LL10
13	Robinson, Brian					DFO					LL11
14	Bugden, Jay					DFO					LL11
15	Wright, Dave					EM&A					LL13
16	Tormey, Sam					NOAA					LL13
17	Susdorf, Gary					ENTRIX					LL14
18	Stroud, Fred					EPA					MD7
19	Devereux, Rich					EPA					MD7
20	Basler, Matt					MACTEC					LL14
21	Smartman, Richard					NOAA					MD6
22	Essex, Laura					EM&A					MD6